# Appendix C: Full Proposal Format and Instruction

- General Instructions

- All proposals must be submitted in English and use a non-serif font type with a readability like that of Calibri, Avenir Next LT Pro Light, Arial, or New Century 11- point font. Smaller non-serif fonts may be used for figures, tables, and charts. Margins should be no less than one inch in width.

- Documents must be clearly labeled with the ISO number, proposer organization, and proposal title/proposal short title (in the header of each page). Use the following Title Format: "TA #, Volume I_XYZ Institution", "Volume II_XYZ Institution", "Volume II Supporting Documents”, etc. Proposals must address one specific Technical Area.

- Conforming full proposals should consist of three volumes as follows plus the Cost Spreadsheet attachment as described:

- Appendix C: Volume I, Technical and Management Proposal,

- Appendix C: Volume II, Cost Proposal, and

- Appendix D: Volume III, Administrative and Policy Requirements Submission

- Attachment 3: Cost Proposal Narrative

- Attachment 3a/b: Cost Spreadsheet

- Summary of Full Proposals Requirements (including page limits):

| Volume 1, Technical and Management Proposal |  |
| --- | --- |
| Volume Element | Page Limit |
| Cover Page | 1 |
| - Executive Summary | 30 |
| - Technical Plan |  |
| - Capabilities |  |
| - Statement of Work (SOW) | N/A, use provided template/format |
| - Schedule and Milestones | N/A use provided template/format in the Model OT |
| - Data Management and Sharing Plan (DMSP) | N/A (estimated 2 pages) |
| - References | NA |

| Volume II, Cost Proposal |  |
| --- | --- |
| Volume Element | Page Limit |
| - Cover Page | 1 |
| - Cost Proposal Spreadsheet(s), including for sub-performers at any tier | N/A, use provided template/format |
| - Cost and Pricing Data Support | N/A |
| - Model OT with proposed changes (recommended, but not required – e.g., no edits suggested) | N/A, use Model OT provided |

| Volume III, Administrative and Policy Requirements Submission |  |
| --- | --- |
| Volume Element | Page Limit |
| Cover Page | 1 |
| - Team Member/Sub-performer Identification | N/A, use provided template/format |
| - OCI Affirmations and Disclosure |  |
| - Research Security Disclosure |  |
| - Novelty of Proposed Work |  |
| - Intellectual Property (IP) |  |
| - Technical Data and Computer Science |  |
| - Patents |  |
| - Ability to Meet Programmatic Goals with IP/Patent Implications |  |
| - Human Subject Research |  |
| - Representations Regarding Unpaid Delinquent Tax Liability or a Felony Conviction Under any Federal Law |  |
| - Software Component Standards |  |
| - Cybersecurity |  |

- Volume I: Technical and Management Proposal

- The maximum page count for Volume I is 30 pages, with exclusions as noted in the table above. ARPA-H encourages conciseness to the maximum extent practicable. No other supporting materials may be submitted for review. Note that while the government’s evaluation of Volume I is limited to the sections included in the page count limitations, it will be reviewing all sections. The other documents may be used to cross-check the proposal and will also inform feedback for proposers whose full proposals are selected in accordance with the evaluation criteria outlined in the ISO for award negotiation.

- At the bottom of Volume I information is a summary of proposal elements recommended for inclusion in proposals based on each TA and track proposed as well as recommendations for all proposals. These elements should be incorporated into the 30-page Volume I submission however the proposer deems it most appropriate.

- Volume I should include the following components:

- Cover Page:

| 1 | Solicitation # |  |
| --- | --- | --- |
| 2 | Full Proposal Title |  |
| 3 | Technical Approach Selection |  |
| 4 | Prime Awardee/entity submitting the proposal |  |
| 5 | Unique Entity Identifier (UEI) of prime proposer/awardee |  |
| 6 | Type of Organization and website URL if applicable | Choose all that apply: Large Business, Small Disadvantaged Business, Other Small Business, Historically Black Colleges and Universities (HBCUs), Minority Institution (MI), Other Educational or Other Non-Profit (including non- educational government entities) (NOTE: The Small Business Administration’s (SBA) size standards determine whether or not a business qualifies as small.). |
| 7 | Date of Submission |  |
| 8 | Technical Point of Contact (POC) | Include salutation Last Name: First Name: Mailing Address: Telephone: Email: |
| 9 | Administrative POC | Include salutation Last Name: First Name: Mailing Address: Telephone: Email: |
| 10 | Other Team Members including consultants, if applicable. | Technical POC Name: Organization: Organization Type: |
| 11 | Total funds requested from ARPA-H, and the amount of resource share (if any) | Total: $ |
| 12 | Place(s) of Performance |  |

- Executive Summary: Provide a synopsis of the proposed project including answers to the following questions:

- What is the proposed work attempting to accomplish or solve?

- How is it done today? What are the limitations of present approaches?

- What are the key technical challenges in your approach, and how do you plan to overcome these?

- What is new about your approach? Why do you think you can be successful at this time?

- Who cares? If you succeed, what difference will it make?

- What are the risks? Identify any risks that may prevent you from reaching your objectives as well as any risks the program itself may present. Please also describe plans to mitigate these risks at a high level.

- How much will your project cost?

- What are your milestones to check for success consistent with ADVOCATE metrics?

- Technical Plan:

Outline and address technical challenges inherent in the approach and possible solutions for overcoming potential problems. This section should provide appropriate measurable milestones (quantitative if possible) at intermediate stages of the program to demonstrate progress, a plan for achieving the milestones, and a simple process flow diagram of the final system concept. The technical plan should demonstrate a deep understanding of the technical challenges, present a credible (even if risky) plan to achieve the program goal, and explain the approaches used to mitigate technical risk.

- TA1 and TA2 proposals should describe:

- Rationale for chosen agentic framework and system architecture;

- Approaches to be applied for agent training, tuning, and grounding;

- Processes to be used in the selection of clinical use cases;

- Rationale for the sourcing and utilization of in-silico benchmarks to track solution clinical performance and safety profile;

- Proposed approach for collaboration with other performers.

- TA3 proposal should describe:

- How TA1 and TA2 will be integrated into the clinical workflow;

- How a feedback loop from patients and clinicians will be established to inform the development of CVD and Supervisory agents;

- How a seamless and effective provision of data and resources for TA1 and TA2 performers to develop and deploy their agentic technologies will be achieved;

- Process to be used for preparation of clinical data;

- Agentic AI governance and continuous improvement processes;

- Approaches used to select, engage, and prepare clinical team;

- Evidence of high-level leadership support for the conduct of study;

- Approach for the sourcing and management of wearables;

- Summary of patient recruitment/engagement plan;

- Proposed approach for collaboration with other performers;

- Broad overview of functions that the health system will allow to be performed by TA1 fully or semi-autonomously during the Scalability Study specifically including the ability to modify existing prescriptions and starting selected low-risk medications;

- Basic features of proposed Scalability Study (e.g., study population, inclusion/exclusion criteria, sample size with power analysis, clinical setting, length of follow-up, etc.);

- Strategy to deploy and evaluate real-world performance of Supervisory agent as a post-market monitoring solution;

- Strategy to collect data that could be used by FDA to assess performance of CVD agent, and post-market monitoring capability of Supervisory agent;

- Ethical review process applicable to institution;

- Provide a plan for the establishment of robust IT infrastructure and dedicated administrative resources for ongoing operations and troubleshooting, with the creation of protocols for critical alerts that are informed by the clinical team for effective AI collaboration;

- Produce an outline for a Scalability Study to assess the effectiveness, safety and scalability of the utilization of both the CVD and Supervisory Agents across multiple clinical settings and patient populations.

- Cybersecurity Strategy:

Deliver a cybersecurity and patient data protection plan strategy describing the approach for securing the data and systems developed as part of the ADVOCATE program as summarized in Appendix A. At a minimum, the proposed strategy must identify the methods and means for implementing access controls, protecting sensitive medical data, securing connections with other systems, safeguarding the agentic AI solution (in particular, its model weights and training data), and responding to cybersecurity incidents. Additionally, please identify the underlying technologies that will be used to ensure this security (e.g. encryption, differential privacy, federating learning, and anonymization).

- Capabilities:

Describe organizational experience in relevant subject area(s), existing intellectual property (IP), specialized facilities, and any government-furnished materials or information. Discuss any work in closely related research areas and previous accomplishments.

- Dissemination Plan for TA3 Performers:

Briefly outline your plan on how to document, systematize, standardize, and disseminate the agentic AI workflow implementation.

- Statement of Work (SOW):

- The SOW should provide a detailed task breakdown and their connection to the milestones and program metrics. Each phase of the program should be separately defined. The SOW must not include proprietary information. Please note, the technical proposal must stand on its own as the SOW cannot be used to supplement the 30 pages of the technical proposal.

- For each task/subtask, provide:

- A detailed description of the approach to be taken to accomplish each defined task/subtask.

- Identification of the primary organization responsible for task execution (performer, sub-performer(s), by name).

- A measurable milestone, i.e., a deliverable, demonstration, or other event/ activity that marks task completion. Include completion dates for all milestones. Include quantitative metrics.

- A definition of all deliverables (e.g., data, reports, software) to be provided to the government in support of the proposed tasks/subtasks.

- It is recommended the SOW be developed so that each phase of the program is separately defined.

- Schedule and Milestones:

Provide a detailed schedule showing tasks (task name, duration, work breakdown structure element as applicable, and performing organization), milestones, and the interrelationships among tasks. The task structure must be consistent with that in the SOW. Measurable milestones should be clearly articulated and defined in time relative to the start of the project

- Data Management and Sharing Plan (DMSP)

- This is recommended to be no more than 2 pages.

- The plan shall demonstrate, on a high level for the proposal stage, how health data will be sourced and preserved while ensuring the integrity of the data collected throughout the period of performance. The plan shall account for addressing that health data that will be collected by performers in the ADVOCATE program will remain confidential and not be subject to secondary analysis or sharing (outside of the government) without the explicit consent of the health data owner.

- For Proposing TA1 teams: the plan must describe how data will be prepared and shared with TA2 performers for solution integration purposes.

- For Proposing TA1 & TA2 teams: the plan must describe how data that will be prepared and shared with the IV&V partner for evaluation purposes.

- For Proposing TA3 teams: the plan must describe how data that will be prepared and shared with the IV&V partner, TA1 and TA2 performers for solution development and evaluation purposes.

- Proposers must provide an explicit plan for timely material, data, and platform exchange between all team members on the proposal, as the free flow of information is critical for the success of the agent development, integration, and deployment. The data should be transmitted frequently, in a timely manner, and in its entirety.

- The DMSP must ensure that the team shares data openly with other performer teams whenever necessary so that agent development, integration, and deployment are not restricted or delayed. All performers will be expected to collaborate with other performers to ensure data handoff and processing is done efficiently.

- Associate Performer Agreement (APA): Provide a signed and dated APA as described in Attachment 2, Article XVIII - Special Terms and Conditions, Section F.

- References:

Include a list with the cited literature.

- Volume II: Cost Proposal

There is no maximum page count for Volume II. The Cost Proposal shall be comprised of the editable Excel Cost Proposal spreadsheet, a cost narrative explaining the proposed costs, and associated supporting materials ideally provided in a single attachment (e.g., Adobe pdf) led by a Cover page as follows.

- Cover Page:

| 1 | Solicitation # |  |
| --- | --- | --- |
| 2 | Full Proposal Title |  |
| 3 | Technical Approach (TA) Selection |  |
| 4 | Prime Awardee/entity submitting the proposal |  |
| 5 | Unique Entity Identifier (UEI) of prime proposer/awardee |  |
| 6 | Type of Organization and website URL if applicable | Choose all that apply: Large Business, Small Disadvantaged Business, Other Small Business, Historically Black Colleges and Universities (HBCUs), Minority Institution (MI), Other Educational, or Other Non-Profit (including non-educational government entities) (NOTE: The Small Business Administration’s (SBA) size standards determine whether or not a business qualifies as small.). Size standards may be found here: https://www.ecfr.gov/current/title-13/chapter-I/part-121#121.201 |
| 7 | Technical Point of Contact (POC) | Include salutation Last Name: First Name: Mailing Address: Telephone: Email: |
| 8 | Administrative POC | Include salutation Last Name: First Name: Mailing Address: Telephone: Email: |
| 9 | Other Team Members (Sub-performers, including consultants) if applicable and type of organization for each | Technical POC Name: Organization: Organization Type: |
| 10 | Total proposed cost separated by base and option(s) (if any) |  |
| 11 | Name, address and telephone number of the proposer’s cognizant auditor (as applicable) |  |
| 12 | Date proposal was submitted |  |
| 13 | Proposal validity period (minimum of 120 days) |  |

- Cost Proposal Spreadsheet:

- ARPA-H Standard Excel Cost Proposal Spreadsheet (See Attachments). All tabs and tables in the cost proposal spreadsheet should be developed in an editable format with calculation formulas intact to allow traceability of the cost proposal. The cost proposal spreadsheet must be used by the prime organization and all sub-performers at any tier.

- While the prime proposer is ultimately responsible for submission of all required documents, sub-performer cost proposal spreadsheets may be submitted directly to the Government by the proposed sub-performer via email to ADVOCATE@ARPA-H.gov. Sub-performers proposals should include Interdivisional Work Transfer Agreements or similar arrangements between the awardee and divisions within the same organization as the awardee.

- Cost and Pricing Data Support:

- In addition to using the cost proposal spreadsheet, the cost proposal must include documentation to support the proposed price/budget. Supporting documentation must be in sufficient detail to substantiate the summary cost estimates and should include a description of the method used to estimate costs (e.g., vendor quotes). For indirect costs provide the most current indirect cost agreement (e.g., Colleges and Universities Rate Agreement, Forward Pricing Agreement, Provisional Billing Rates, etc.).

- Cost and pricing support may also facilitate a value analysis by the government through information other than detailed cost and pricing data. Proposers are encouraged to include information related to value added resources or conditions that are not immediately obvious in the Cost Proposal Spreadsheet or the traditional forms of cost and pricing support information like vendor quotes (e.g., intended intellectual property terms and conditions with perceived future value).

- Model OT:

Proposers may suggest edits to the model OT for consideration by ARPA-H and provide a copy of the model OT with track changes (i.e., ‘Redlines’) as part of the full proposal package. Proposers must include comments providing rationale for any suggested edits of a non-administrative nature. Suggested edits may be rejected or negotiated at ARPA-H’s discretion.

Submission of proposed edits to the Model OT will facilitate more efficient negotiations.

- Volume III: Administrative & National Policy Requirements Document Template

- The Administrative and National Policy Requirements document must be completed in full. Do not delete any portion of this document.

- All pages shall be formatted for printing on 8-1/2 by 11-inch paper with 1-inch margins and font size not smaller than 11-point. Font sizes of 8- or 10-point may be used for figures, tables, and charts. There is no page limit for this document.

- The Administrative and National Policy Requirements document must be in .pdf, .odx, .doc, or .docx formats. Submissions must be written in English.