# APPENDIX E: ADVOCATE Commercialization Roadmap

The commercialization roadmap below has been created as a guide to address commercialization-related activities. These activities may not be relevant or appropriate for all proposers. Proposers may suggest adjusted or alternate activities that align to their technical approach and relevant transition and commercialization strategy.

| FY26 | Phase 1A |
| --- | --- |
| End User/Market | - Initial adopters for downstream pilot deployment identified - Voice of customer analysis to ID workflow integration challenges and opportunities completed - Voice of customer analysis to understand cost constraints completed - EHR and wearables providers to understand integration potential and data access identified and initial partnerships for downstream integration and piloting established (Phase 2) - User Interface/User Experience (UI/UX) testing with Minimum Viable Product (MVP)/prototype with patients and clinicians through patient groups and TA3 health systems initiated - IT security questionnaire launched to capture privacy, security and other requirements for standardization |
| Business Model | - Competitive landscape monitoring established - Business model strategy includes reimbursement strategy (inc. Centers for Medicare & Medicaid Services (CMS) engagement), value capture options, and monetization pathways established |
| IP | - IP assets identified and categorized. IP risk assessment and patent filing timeline completed. Process to secure legal protection along with IP strategy and management planning established - Open-source requirements and/or licensing model between TA 1 and 2 performers determined |
| Regulatory | - Regulatory roadmap to include intended use(s), certification process, safety and efficacy data needs, and clinical endpoint requirements provided. - TA 1 performers to hold 513g meetings with FDA - TA 2 performers to meet with FDA Medical Device Development Tools (MDDT) team - Submit plan for FDA Investigational Device Exemption (IDE) studies |
| Exit Plan | - Investor strategy provided to include engagement with investor community and strategic discussions to optimize for downstream funding |
| FY27 | Ph Phase 1B |
| End User/Market | - UI/UX testing plan for pilot deployment prepared - Initial Go-To-Market (GTM) planning and strategy mapping established |
| Business Model | - Business model and proposed pricing structure for model, in alignment with strategic partnership conversations established - Standard business associate agreements prepared to address privacy and security |
| IP | - Inter-performer IP arrangements required finalized |
| Regulatory | - Submit plan with TA 3 systems for scalability study - Begin FDA IDE studies for TA 1 |
| Exit Plan | - Updated strategic investor engagement plan provided |
| FY28-29 | Phase 2 |
| End User/Market | - UI/UX testing report based on feedback received in Phase 1A/B completed - Scalability study executed with strategic partners (TA3, other) |
| Business Model | - Negotiation of commercial contracts with TA3 health systems or other strategic partners established - Finalize reimbursement/coding strategy provided |
| Regulatory | - System architecture design specifications and SaMD / IDE documentation provided - IDE submission summary results submitted |
| Exit Plan | - Ownership summary of all anticipated assets provided - Strategic partnerships are in place to de-risk downstream adoption |
| Final | Final Commercialization Plan / Transition |
| Product Development | - All previous annual commercialization plans included - Clinical development plan provided |
| Business Model | - Health Economics and Outcomes Research data analysis results provided |
| IP | - IP summary including all IP ownership locked and licensing terms outlined |
| Regulatory | - FDA submission and communication updates provided |
| Exit Plan | - Investor summary with at least 1 strategic partnership and/or acquisition interest for transition outlined - Exit plan summary of all assets to be transitioned - ADVOCATE playbook created to capture TA1-TA2 implementation for scaled clinical settings as well as how regulatory and clinical outcomes will be reported and measured for reimbursement and value proposition |